## Execute and Monitor Project Plan

Keep this as a rhythm: daily quick checks, weekly formal updates (update % complete), and monthly steering reviews.

### 1 Update % Complete with current task status

Daily/Weekly Inputs: Actual work done (hours), completed task items, actual start/finish dates.
Steps (GanttProject):

- Right-click task → Properties (or double-click) → set % Complete. You can also set Actual Start / Actual End if the tool supports.

Example status (Week 6):

- Requirements = 100%

- Design = 100%

- Implementation = 50%

- Testing = 0%

- Deployment = 0%

- Output: Gantt progress bars reflect current status.

### 2 Review the status of each task

Steps:

- Sort or filter tasks by Status (Not started / In progress / Complete).

- Generate a task status table (Task, Owner, %Complete, Start, End, Days Late).

  Green (on track): Requirements, Design

  Yellow (in progress): Implementation

  Red (not started): Testing, Deployment

Output: Task status log (weekly).

### 3 Compare Planned vs Actual Status (Earned Value approach)

### Goal: Compute PV, EV, AC and variances

### Compare Planned vs Actual Status

- Planned EV = 60%

- Actual EV = 50%

- Behind schedule (SPI < 1).

Output: EV table + interpretation (on track / behind / over budget).

### 4 Review the status of Critical Path

Tool method (preferred):

- In GanttProject look for a Critical Path view or option (often under View or Tools). Enable it — those tasks typically appear highlighted (red).

- Critical path = Requirements → Design → Implementation → Testing → Deployment.
 If Implementation slips, whole project slips.

Manual method: Tasks with zero float are critical. To compute float manually you need a forward/backward pass (tool like MS Project automates this).
Action: For each critical task, check %Complete and remaining work. Any late critical task pushes the project finish date escalate immediately.
Output: Critical tasks list, corrective actions logged.

### 5 Review resource assignation status

Steps (GanttProject):

- Open Resource load or Workload view. Identify overallocated resources (bars above capacity / red icons).

- If overallocated, reassign tasks, adjust schedule, or split tasks.

- Output: Resource overallocations identified & mitigation plan.