# Generate Dashboard & Reports from GanttProject

## Step 1: Export Data from GanttProject

- Open your project in GanttProject.

- Go to File → Export.

  - Export Task Data → CSV (includes tasks, dates, % complete).

  - Export Resource Data → CSV (includes resource list).

  - Export Assignments → CSV (task-resource-hour allocations).

- Save all exports into a project folder (e.g., /SPM_Reports/).

These 3 files will be your raw data for reports.

## Step 2: Build the Dashboard (Excel / Power BI)

### Sections to Include:

#### 1. Project Overview (Top Cards)

- Fields: Project Name, Project Manager, Report Date, % Complete, SPI, CPI, BAC, EAC.

- Formulas (Excel):

  - %Complete = EV / BAC

  - SPI = EV / PV

  - CPI = EV / AC

  - EAC = BAC / CPI (basic formula)

- Conditional Formatting:

  - Green: SPI ≥ 0.95 and CPI ≥ 0.95

  - Amber: 0.90–0.95

  - Red: < 0.90

Dashboard Cards Example:

| Metric | Value | Status |
| --- | --- | --- |
| %Complete | 52% | Green |
| SPI | 0.92 | Amber |
| CPI | 0.85 | Red |

#### 2. Cost Overview (S-Curve)

- Chart: Line Chart with 3 series → PV, EV, AC (cumulative values).

- Add BAC (Budget at Completion) and EAC as reference lines.

Output: S-curve showing Planned vs Actual vs Earned trend.

#### 3. Upcoming Tasks (Table)

- Filtered on tasks where:
StartDate BETWEEN ReportDate AND ReportDate+7

- Columns: Task, Owner, Start, End, %Complete, Risk.

Output: Table of next week’s planned work.

## Step 3: Resource Reports

### 1. Over-allocated Resources

- Columns: Resource, Role, AssignedHours, AvailableHours, Utilization%.

- Formula: Utilization% = AssignedHours / AvailableHours * 100.

- Highlight >100% in red.

### 2. Resource Overview

- Columns: Resource, Role, CurrentTasks (COUNT), Next Available Date, TotalCostToDate.

- Formula: TotalCostToDate = AssignedHours * Rate.

## Step 4: Cost Reports

### 1. Earned Value Report

- Columns: PV, EV, AC, SV, CV, SPI, CPI, BAC, EAC, TCPI.

- Formulas:

  - SV = EV – PV

  - CV = EV – AC

  - SPI = EV / PV

  - CPI = EV / AC

  - TCPI = (BAC – EV) / (BAC – AC)

### 2. Resource Cost Overview

- Columns: Resource, Rate/hr, AssignedHours, Cost = Rate × Hours, Variance.

### 3. Task Cost Overview

- Columns: Task, BaselineBudget, EV, AC, CV, Notes.

- Sort by largest negative CV (biggest cost trouble).

## Step 5: Progress Reports

### 1. Critical Tasks

- Columns: Task, Owner, %Complete, RemainingWork, Slack/Float, Impact.

- Identify tasks on critical path (from GanttProject view).

### 2. Milestone Report — Slipping Tasks

- Columns: Milestone, PlannedDate, ForecastDate, DeltaDays, TasksCausingSlip, CorrectiveAction, Owner.

- Formula: DeltaDays = ForecastDate – PlannedDate.

- Flag milestones with slip > 0 days.

## Step 6: Assemble Reports into One Deliverable

- Create a single Excel file with sheets:

  - Dashboard (cards, charts, KPIs)

  - Resource Reports

  - Cost Reports

  - Progress Reports

- Or in Power BI:

  - Import CSV exports

  - Create visuals (cards, line charts, tables with filters)

  - Use slicers (e.g., by Date, Resource, Task Owner).